## Resource Calc
Module wise Effort in Person Days
Module | Property Tax | Fire NOC | PGR | Water & Sewerage | Trade License | OBPAS | User Charges | Municipal Finance | Birth & Death | Web Portals | DSS / Dashboard
Requirements | 60 | 15 | 15 | 45 | 30 | 120 | 15 | 120 | 30 |  | 30
Localization and Language | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Basic product setup | 20 | 10 | 10 | 20 | 20 | 20 | 10 | 20 | 20
Standardisation of masters | 30 | 15 | 15 | 30 | 15 | 60 | 10 | 60 | 15
Setup of categories / masters | 30 | 15 | 15 | 30 | 30 | 60 | 5 | 60 | 30
Setup of workflows / role action mapping | 30 | 15 | 15 | 30 | 30 | 310 | 15 | 310 | 30
Data indexing | [10 empty] | 15
Connecting with other modules | [10 empty] | 15
Data collection | [9 empty] | 60
Data standardisation | [9 empty] | 30 | 30
Basic product setup | [9 empty] | 10 | 30
Mobile responsiveness | [9 empty] | 10
Map integration | [9 empty] | 10
Approval workflow for BPA | [5 empty] | 60
eDCR setup | [5 empty] | 60
eDCR rules setup | [5 empty] | 310
Structural drawings preparation
Custom reports (2) | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Integration (ABAS + any other) | 15 | 0 | 0 | 5 | 15 | 15 | 15 | 15 | 15
Total Dev & Setup | 200 | 85 | 85 | 175 | 155 | 1030 | 85 | 600 | 155 | 120 | 120
QA | 80 | 34 | 34 | 70 | 62 | 412 | 34 | 240 | 62 | 48 | 48
UAT support + final data setup | 125 | 46.5 | 46.5 | 125 | 50 | 15 | 50 | 15 | 50 | 100 | 75
Rollout (training, documentation, demos, local tech support training) | 100 | 50 | 50 | 100 | 100 | 150 | 50 | 150 | 100 | 50 | 25
Total (Person-Days) | 505 | 215.5 | 215.5 | 470 | 367 | 1607 | 219 | 1005 | 367 | 318 | 268
Person Months | 25.25 | 10.775 | 10.775 | 23.5 | 18.35 | 80.35 | 10.95 | 50.25 | 18.35 | 15.9 | 13.4
Grand Total Person Months |  | 277.85
High Customization Implementation | 80% | 500.13
Medium Customization Implementation | 60% | 444.56
Low Customization Implementation | 40% | 388.99
Above effort is estimated for 100 ULB (Urban Local Body) implementation for different degrees of customisation
Effort multiplication factor for -
250 ULBs | 1.5x
500 ULBs | 2.7x